## Лист1
TEST PLAN
INTRODUCTION: | AUTHOR:
Testing Notepad Version 1803 | HYZHA OLHA
IN SCOPE: | OUT OF SCOPE:
• application launch/close • file operations: - create - open - save/save as • text operations: - manual input - cut/copy/paste/delete - undo - find/find & replace - select all • text view: - word wrap - font/style/size | • functions - print - change print parameters • help/about
RISKS:
• printing problems • incorrect help/about information
ENVIRONMENTS AND TOOLS:
• PC or Desktop with installed Windows based OS
RESOURCE:
• middle QA - 1
• junior QA - 1
TIME SCALES:
• 1 day
ENTRY CONDITIONS: | EXIT CONDITIONS:
• application is available for testing | • all in scope testing should be completed
• no testing 'Blockers' | • all issues detected during testing are reported